## user task status
Index | user | requestDate | requestBy | daysLeft | taskDone | taskOnGoing | taskPending | monthTaskDoneInTotal | monthTaskOnGoingInTotal | monthTaskPendingInTotal | monthTaskDoneInMonth | monthTaskOnGoingInMonth | monthTaskPendingInMonth | tasks | taskTotal | statusInfo
1 | Phong | 2024-08-06 09:55:01.018 |  | 24 | 0.35 | 0.6 | 0.05 | 0.3 | 0.05 | 0.05 | 0.75 | 0.13 | 0.13 | * | 8 | Task status of July Tasks of user Phong Project Lorem Ipsum is simply dummy: Task fix even more bug(41 days) status: Task is done very late, 24 days until deadline Task implement create method(41 days) status: Task is ongoing, 24 days until deadline Task get specification(41 days) status: Task is done early, 24 days until deadline Task 2 get more specification update(41 days) status: Task is done extremely late, 24 days until deadline Task design(41 days) status: Task is done extremely late, 24 days until deadline Task lai design(41 days) status: Task is done extremely late, 24 days until deadline Task build db(39 days) status: Task is done early, 24 days until deadline Task demo(39 days) status: Task is pending, 24 days until deadline 55% tasks done 9% tasks on going 9% tasks pending Tasks of user Phong Project project thang 4: 0% tasks done 0% tasks on going 0% tasks pending Tasks of user Phong Project project thang 5: 0% tasks done 0% tasks on going 0% tasks pending Tasks of user Phong Project project thang 6: 0% tasks done 0% tasks on going 0% tasks pending In total of July, there are: 30% tasks done 5% tasks ongoing 5% tasks pending

## taskStatusByUser
Index | timesheetId | task | createdDate | startDateExpected | actualStartDate | finishDateExpected | actualFinishDate | result | note | details | status | projectId | createdBy | lastUpdate | assignedUser | subTasks | daysLeft | progressByTime | description | taskComment | progressBySubTask
1 | 14 | fix even more bug | 2024-07-18 10:56:31.0 | 2024-07-20 10:56:31.0 | 2024-07-26 10:56:31.0 | 2024-07-25 17:58:19.0 | 2024-07-29 17:58:19.0 | none | have to do fix even more bug of project project new dang test 3 | none | 2 | 8 | none | 2024-07-22 17:12:15.0 | none | ** | 24 | 0.41 | Task is done very late | Task is done very late | 1
2 | 18 | implement create method | 2024-07-17 17:28:25.0 | 2024-07-20 17:58:19.0 | 2024-07-26 06:00:00.0 | 2024-08-26 17:58:19.0 | none | none | have to do implement create method of project project new dang test 333 | none | 1 | 8 | none | 2024-07-17 17:28:25.0 | none | demo lan 1, demo lan 2, demo lan 3, demo lan cuoi, demo lan cuoi 2 | 24 | 0.41 | Task is ongoing | Task is ongoing | 0.8
3 | 22 | get specification | 2024-07-17 17:33:25.0 | 2024-07-20 17:58:19.0 | 2024-07-19 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-07-20 17:58:19.0 | none | have to do get specification of project project new dang test 333 | none | 2 | 8 | none | 2024-07-17 17:33:25.0 | none | ** | 24 | 0.41 | Task is done early | Task is done early | 1
4 | 23 | 2 get more specification update | 2024-07-18 09:51:46.0 | 2024-07-20 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-08-21 17:58:19.0 | good | have to do get more specification of project project new dang test 333 | none | 2 | 8 | none | 2024-07-18 10:38:46.0 | none | ** | 24 | 0.41 | Task is done extremely late | Task is done extremely late | 1
5 | 24 | design | 2024-07-18 09:51:46.0 | 2024-07-20 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-08-21 17:58:19.0 | good | have to do design of project project new dang test 333 | none | 2 | 8 | none | 2024-07-18 10:50:01.0 | none | ** | 24 | 0.41 | Task is done extremely late | Task is done extremely late | 1
6 | 25 | lai design | 2024-07-18 09:51:46.0 | 2024-07-20 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-07-21 17:58:19.0 | 2024-08-21 17:58:19.0 | good | have to do design of project project new dang test 333 | none | 2 | 8 | none | 2024-07-18 10:50:47.0 | none | ** | 24 | 0.41 | Task is done extremely late | Task is done extremely late | 1
7 | 26 | build db | 2024-07-18 10:56:31.0 | 2024-07-22 17:58:19.0 | 2024-07-18 10:56:31.0 | 2024-07-29 17:58:19.0 | 2024-07-28 17:58:19.0 | none | have to do build db of project project new dang test 333 | none | 2 | 8 | none | 2024-07-18 11:00:46.0 | none | ** | 24 | 0.38 | Task is done early | Task is done early | 1
8 | 32 | demo | 2024-07-22 09:25:16.0 | 2024-07-22 17:58:19.0 | none | 2024-07-29 17:58:19.0 | none | none | No response from user | have to do demo of project project new dang test 333 | 0 | 8 | none | 2024-07-22 09:25:16.0 | none | ** | 24 | 0.38 | Task is pending | Task is pending | 0